August 2021

Contents

1	Action Plan								3

2	Improvement Projects						7

3	Outcomes Framework						8

4	Risk and Issues Log							9

Appendix 1 – Prioritisation Workshop					10

1	Action Plan

| Workstream​ | Key Actions​ | Lead Responsibility​ | Timescale​ | RAG​ | Notes/ progress​ |
| --- | --- | --- | --- | --- | --- |
| Locality Planning | Evaluation of Locality Empowerment Groups to provide baseline engagement Oversee transition to new integrated locality planning model and production of community led locality plans following Phase1 Review of Locality Planning Locality Empowerment Groups/ Priority Neighbourhood Partnerships - Community Connectors/ Community Ideas Oversee Phase 2 Review of Locality Planning – Connecting with wider communities | Shamini Omnes, ACHSCP Michelle Cochlan, ACC Shamini Omnes, ACHSCP Colin Wright, ACC Gordon Edgar, AHSCP Rachel Harrison, ACC Michelle Cochlan, ACC | May 21 July 21 Ongoing October 21 |  | Infographic and benefits maximisation framework shared with members. Provides an example of how we might evaluate progress against our strategy. Complete Recruitment needed in South and Central LEGs. Also need to ensure all LEGs are representative of the diverse communities and groups in the localities. Community connectors are being identified to link into LOIP projects. All community reps have a role in promoting and raising awareness of the opportunity. Jade Leyden has produced a video for Torry to be shared with and used by communities. Need to be more proactive on recruitment acknowledging there are resource challenges at the moment. Not yet started. Need to prepare Terms of Reference. |
| Connecting Communities into Community Planning Aberdeen | Increased community engagement in the refresh of the LOIP via the public values simulator Engaging with community groups and connectors on simulator results and draft LOIP/ Locality Plans Development of Aberdeen Responsible Business Community Network Strengthen role of funded groups/ participatory budgeting/ FAF as community connectors Quarterly Extended Community Empowerment Group Meetings | Martin Wyllie, ACC All Michelle Cochlan, ACC Maggie Hepburn, ACVO Tanita Addario, ACC Maggie Hepburn, ACVO Susan Thom, ACC Michelle Cochlan, ACC Jonathan Smith, Civic Forum Maggie Hepburn, ACVO | March 21 May to July 21 October 21 TBC Sep 21 |  | Complete. Results considered by OIGs and LEGs/ PNPs in developing the LOIP/ Locality Plans. Complete. Identification of community connectors ongoing. Online CSR platform launched October 20. Follow up event to be held 25 Nov 21. Roots to sustainability work. Claire Shaw Funding Officer will be picking this up. Meeting to be arranged. ACVO producing promotional materials |
| Engagement, Participation & Empowerment Strategy | Review of the current Engagement, Participation and Empowerment Strategy. Including: Review terminology around seldom heard/ hard to reach groups and revise details of these groups Review to include analysis of current reach into communities. E.g. protected characteristics, harder to reach groups. National Standards for Community Engagement? Action TBC PB as a tool | Dave Blac, GREC Fiona Clark, ACC Maggie Hepburn, ACVO Darren Bruce, PS | Sep-Dec 21 |  | Review rather than overhaul Tangible/ useful Live resource online Case studies kept fresh How success will be measured Manageable size Launch pad SCDC Exercise has been initiated by Dave through Equalities Participation Group |
| Community Learning and Development Plan | Review governance arrangements for CLD to address feedback from last CLD inspection and confirm role of CEG Development of Revised CLD Plan | Fiona Clark, Aberdeen City Council Colin Wright | September 21 September 21 |  | Workshop held to understand current challenges. Follow up meeting with Caroline Johnston to be arranged by Fiona. It was agreed the CEG will be responsible for monitoring overall strategy and Partnership Forums will oversee delivery on the ground. Draft plan developed and out for consultation. |
| Participation Requests and Asset Transfer | Support for communities to make participation requests/ asset transfer | Maggie Hepburn, ACVO Wendy Henderson, Independent Sector | TBC |  | Looking at what other areas are doing on this |
| Share and Explore Innovation and Best Practice in Community Empowerment | Online Simulator Place standard tool? Action TBC Community Voices | Martin Wyllie Colin Wright, Aberdeen City Council Martin Wyllie | Adopted TBC Ongoing |  | Martin working with the CLD team to progress. |
| City Voice | Oversee production of next City Voice Questionnaire to support availability of LOIP/ Locality Plan data and Community Empowerment | Anne McAteer, Aberdeen City Council | June/ July 21 |  | Underway. Survey to close and results analysis available October. |

2	Improvement Projects

| Aim​ | Rationale​ | Project Manager​ | Changes ​ | Data​ |  |
| --- | --- | --- | --- | --- | --- |
| Increase the number of responsible businesses working with Community Planning Aberdeen through Community Benefits and CSR activity by 200% by 2023 (Approved as new LOIP project in September 2021) | ​Strengthen links with responsible businesses across the City to align corporate social responsibility efforts with the priorities within the Local Outcome Improvement Plan. | ​Tanita Addario | - ​CPA Aberdeen Responsible Business Platform - Aberdeen CSR Network - Recognised Aberdeen Responsible Business Partners - Lead contact for liaising with businesses - Aberdeen Responsible Business Event | Baseline Data: No. businesses pledging commitment to CPA No. businesses collaborating with CPA No. digital devices donated by businesses No. business enquiries about working with CPA Total no. attendees at CPA business events Financial contributions from businesses | 8 7 40 11 92 £26,900 |

3	Outcomes Framework

The following indicators of community empowerment will be incorporated into the Aberdeen Outcomes Framework https://communityplanningaberdeen.org.uk/outcomesframework/

Initial indicators to be identified but will also be considered as part of the review of the Participation, Engagement and Empowerment Strategy.

| Indicator | Baseline | Current​ | Trend ​ | Action/ Improvement Project |
| --- | --- | --- | --- | --- |
|  | ​ | ​ | ​ | ​ |

4	Risk and Issues Log

| Control Strength: | A | Working effectively | B | Requires development | C | Not effective | D | Broken down |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Risk | Controls | Control Owner | Strength | Improvement Actions | Timescale |
| --- | --- | --- | --- | --- | --- |

Appendix 1	Community Empowerment Group Workshop