Resilient, Included and Supported (RIS) Outcome Improvement Group

Meeting: 23th November 2023 at 2.30 pm

Agenda

Attendees: Alison MacLeod (Chair), Grace Milne, Danny Ruta, Rachel Harrison, Andrew Hislop, Leone Craig, Rachel Barclay, Jonathan Davis, Andrew Falconer, Andrinne Craig, Jane Russell, Michelle Crombie

Apologies:  Chris Smillie,

| Item No. |  |
| --- | --- |
| 1 | Welcome and Apologies Alison welcomed all to the meeting and introductions were made for the benefit of Rachel Barclay who had joined the Group now Jonathan was moving onto a new post. Alison welcomed Danny Ruta who was in attendance to speak on Item 6. |
| 2 | Note of meeting 12th October 2023 Approved as an accurate account of the meeting. |
| 3 | Matters Arising from previous minute No matters outstanding to be addressed. |
| 4 | Dashboard – Stretch Outcome 11 All project managers are asked to consider the following questions when providing their project updates to inform our feedback to the CPA Management Group. - Are we gathering/providing data to show the impact of the changes being tested and towards the overall aim? - Are the changes and pace of testing likely to achieve the overall aim, or are there other changes that can be tested - Are PMs using their multi-agency project teams to test the changes and not acting alone? - Are there any key outcomes/achievements for highlighting to the MG? To be provided by next Management Group meeting. - Are there any further issues for highlighting to the MG, or any that can be removed? - Communication - how are you promoting your projects? – Link to CPA comms help sheet |
| 5 | Stretch Outcome updates |
|  | - 11.1 - Suicide prevention project: - Jonathan advised that he was updating the Project End Report and will have that submitted soon. Rachel Barclay will be taking over suicide, vulnerable adults and Adult Mental Health. Barry Stewart was moving on to a new post and Mark Young was taking on Barry’s role. Aberdeen stats are encouraging and lower than they have been for some time at 4 deaths per 100,000 for the last quarter, and it appears the work taking place seems to be having an impact. - Alison thanked Jonathan for all his support on the project. Although the original aim has not been met the situation could be worse if all the work being done was not in place. |
|  | - 11.2 - Volunteering Opportunities: Closed & Project End Report submitted |
|  | - 11.2 - Volunteering Opportunities: Closed & Project End Report submitted |
|  | - 11.3 - Promote Wellbeing and Good Health Choices: Closed & Project End Report Submitted |
|  | - 11.4 - Reducing Tobacco Smoking: Closed & Project End Report submitted |
|  | - 11.5 - Youth Homelessness: - Rachel has taken over the role from Graeme and did not have an update but will be able to give this at the next meeting. She indicated that there has been an increase in homelessness across the city. - Grace offered to support developing the Project End Report to meet the deadline. - ACTION: Rachel will meet up with Grace and Leone. |
|  | - 11.6 - Unpaid Carers: Closed & Project End Report submitted. - Andrew can’t attend the Board meeting, however Anna Schmitt will attend in his place. |
|  | - 11.7 - Whole Systems Approach to Healthy Weight: - Leone said there was a meeting at the beginning of November which unfortunately she had been unable to attend. No further meetings are in place. It has proved very challenging to engage with families. If this project was to go forward there would need to be a new Lead in place as Tracey was not keen in continuing. - The Project End Report requires to be submitted to the February meeting. - ACTION: Grace will look over the Project End report to ensure it ready to submit to the February meeting. |
|  | - 11.8 - COPD Referrals into PR: Closed & Project End Report submitted. |
| 6 | Whole System Approach to Obesity Danny Ruta was in attendance and shared information on the whole system approach to obesity that he was involved in and confirmed that this has a link to healthy life expectancy. He said obesity was a bit like a pandemic and the death toll related to this could be huge and as such needs to be addressed. Obesity causes 23% of all deaths in Scotland which is more than is caused by smoking. It costs NHS Scotland around £600m a year. It had been concluded that this was not caused by lack of physical activity but that the underlying cause was the environment we live in particularly the high fat ultra processed food around us. He indicated that around 12k adults were overweight in Aberdeen City with 35k adults being obese. Childhood obesity is more worrying if nothing changes. Danny went on to explain the solutions and what could be done at the government level and at NHS level and the paper attached includes this and all the information Danny shared. Planning legislation around where fast food outlets could open was important. Danny shared information on work that he had undertaken whilst working in a previous post in London, although they did not reduce the childhood obesity it did level off. Amsterdam took a whole system approach and did manage to reduce childhood obesity by 12%. He felt that it was good to continue to work on having a whole system approach and he shared a list of various planning that could be put in place. He said that the Shire was one of Scotland’s pilots to have a whole systems approach. He felt the Community Planning Partnership was the vehicle to take this approach forward and suggested we learn from what the Shire has done and take the ‘Leeds Beckett toolkit’ and set up a Healthy Eating, Healthy Living Partnership which could take at least five years before one can start seeing the obesity rates come down. Alison said that senior leaders were the key stakeholders in this and that this would not be easy. She went on to explain that it had been considered whether this could be a project for the RIS, however it had been discussed that this needs to be a stretch outcome on its own. Jonathan commended Danny for taking on this work and felt it was a culture change that was required such as was with drink driving. He drew attention to the education system and how they come out of school and there are no healthy food outlets for them to go to. Jonathan offered to give any support he could. Leone asked what the plan was and where it currently was. Danny said this was just starting and shared information saying there needs to be an Action Plan to address the balance and that process could take 18 months. Following that you need to prioritise certain themes with sub-groups. Leone shared the approach they had taken with the outcome they were involved in and offered to give support. She could engage students to give some background support. Andrinne said Sport Aberdeen would be glad to give support and asked if Danny could give the presentation to colleagues within Sport Aberdeen. ACTION: Andrinne will put Danny in touch with the lead on the ‘Daily Mile’ for schools. Rachel raised social media and how we engage via that and Danny confirmed this was imperative to engage with, and drew attention to the anti-smoking campaign. Alison thanked Danny for the useful presentation. Michelle had joined the meeting late and said she will catch up with Danny and Alison later regarding the presentation. Danny had contacted Angela Scott to discuss whether Obesity could be a Stretch Outcome on its own. Michelle confirmed that the RIS could oversee an outcome with this focus and develop it. Leone drew attention to 11.7 which was a whole system approach to healthy weight which was what Danny was proposing. Danny confirmed that the CPP Board needs to take ownership and shared the necessary changes that required to take place at the same time and the need to engage the right level of senior leadership of all partners to make a difference. Further discussion took place on where this would sit and whether it was too large to sit within RIS. Alison said it would require to have the right people involved to meet the outcome with stakeholders around the table. Alison concluded that there was further discussion required to consider how best to approach this. Michelle left the meeting. |
| 7 | LOIP Refresh Alison shared on the screen the revised outcomes and spoke to each. Homelessness was no longer included as an outcome for this Group as it is anticipated this will be a standalone outcome within the refreshed LOIP. Comments have been received from the Management Group and Alison had included these. Timescales were required for each aim, along with baseline data. There was also a need for suggestions around lead partners and Alison highlighted these. Grace advised that baseline, timescales and lead partners need to be agreed for the 11th December. Jonathan said that SAMH will not take a lead on Suicide Prevention, and it may not be the police so a Lead needs to be confirmed. He suggested making contact with Liam Yule at SAMH. ACTION: Grace to contact Liam Yule at SAMH. ACATION: The revised outcome paper be circulated as is and all asked to come back by the deadline in the email which will clarify the ask. |
| 8 | AOCB No further business discussed. |
| 9 | Next meeting - 17th January at 2 pm |