Sustainable City Outcome Improvement Group

Meeting on Teams 4th April 2023

Present: Daria Shapovalova, Debjani Sarkar, Jacqui Bell, Jillian Evans, Joanna Murray, Joanne Riach, Mike Elder (fire service), Sandy Gustar (ACC), Steven Shaw, Sue Lawrence.

Actions:

- SO15 meeting to progress ideas and consider SC input later this month. Other members are welcome to join

- Jacqui to link Daria and Allison about community engagement project team

- Project leads - please complete the baseline questionnaire on community engagement

- Debjani to share stories from green champions

- Share any ideas on ways to pass on unused uncooked food (email Jacqui or Debjani)

Warmth on Prescription

- Trial undertaken throughout the winter to offer heating costs to be refunded for people whose health is at risk from living in a cold home.  Trial in partnership with Energy Systems Catapult https://es.catapult.org.uk/ SCARF and NHSG.  Over 500 people in Aberdeen and North Aberdeenshire have benefited from this.

- Evaluating with uptake, impact and experience in collaboration with Sheffield Hallam University and DaSH UoA.

- Would like to extend this beyond this winter pending evaluation and other possibilities e.g. Shire, where many use oil for heating

- We were one of 3 trial sites in UK and had better uptake compared with other trial partners.

- David from SCARF will say more another time.

Stretch Outcome 15

- Small group met to decide how to progress with new change ideas:

  - Develop a marketing campaign involving partners across the City

  - Seek case studies on land use from different areas e.g. education, health, business (land element of green prescribing could fit here)

  - Data collection with baseline - 1. citizen science with support from Hutton, BioD project, NatureScot - test ideas and work up to a campaign later in the year; 2. social media e.g. test with 'no mow may'; 3. City Voice - develop a set of questions

  - Existing work - No Mow May, Beelines, Meadows in a box, Keep Scotland Beautiful connection, Wee forest

- Who is target audience? Public land/private companies – need different approaches

- What does the target of 26% of land for nature mean? Need more of a steer.

- Daria offered support as chair of Ukrainian hub in Aberdeen

- Suggestion to use photos of butterflies – for campaign and monitoring

- https://www.plantlife.org.uk/campaigns/nomowmay/

- NHSG grounds staff taking part in No Mow May on 10 sites with before/after photos

- NHSG have eco/biodiversity survey from 2021 – Aberdeen sites

Community engagement

- New Community Empowerment Strategy by Community Planning

- Stretch Outcome 16: 100% increase in the proportion of citizens who feel able to participate in decisions that help change things for the better by 2026

- Daria is looking at indicators to measure community engagement – willing to join the project group

Other updates

- Waste – continuing conversations with ACC team on working together.

- Green champions – meetings with other local organisations and other councils; in NHSG focus is on clinical colleague involvement. Suggestion of using stories to inspire others – does it increase uptake?

- No Food Waste Day – catering teams in NHSG. May use bite-size videos to promote. Also action in ACC carbon plan. May take to schools. Need to find ways to pass on unused uncooked food. (Cooked food not possible)

Next meeting: Thursday 18/05/2023 9:30-11:00 AM

We plan to consider active travel and more about Warmth on Prescription. Please contact Jacqui or Jillian with any other agenda items.