Sustainable City Outcome Improvement Group

Meeting on Teams 4th October 2022

Present: Allison Swanson, Andrew Baxter, Daria Shapovalova, Jacqui Bell, Jillian Evans, Joanna Murray, Joanne Riach, Sue Lawrence, Fiona Mann, Maggie Hepburn, Pam Walker, Sophie Beier.

Apologies:  Sinclair Laing, Kelly Wiltshire, David Dunne, Steven Shaw

We received the sad news that one of our members, Ann Wakefield, passed away over the summer. She was a valuable member of our group and we will miss her. A condolence card will be sent.

Follow-up from last meeting

- Steven is writing a plan for continuation of green spaces work that will be shared

- Joanne has been continuing to follow up on NHS land for food growing

- Jillian will explore with NHS chief execs on signing up to the Biodiversity pledge

Rapid testing (Allison)

- Tests of change are expected to be a series of small steps - 30 days maximum

- Impact needs to be measured and reported – where needed this can be used to argue for changes beyond the reach of the project

- See slides attached

Waste (Pam and Andrew)

- Intention to use SC group to add value to existing waste projects e.g. RESUSE shop

- Also for waste team to add value to other SC LOIP projects

- Extending network for comms and data gathering e.g. ACC green champions

- Mapping interventions  / Needing input from CFINE

- Suggestion to incorporate other ideas for tests of change e.g. bike recycling scheme

- Jillian to meet with Andrew and perhaps NHSG waste team to consider including other partners in the project team

Resilience (Fiona)

- Resilience group in Bridge of Don has stalled temporarily (as being supported by Culter group) but initial meetings over the summer have confirmed enthusiasm and commitment

- More organisations have joined (Rotary Club and First Responders)

- Should this pilot prove successful approach may be tried in other areas of the city

- Press statement and emails to community centres are nearly ready for circulation

- Intending to employ a community resilience officer using funding from an energy company

- Using same funding to purchase specialist battery packs

- Working on aligning utilities databases with ACC

- Draft ‘Persons at Risk’ database for use in emergency responses ready by the end of October

- IMT set up for winter preparedness

Just Transition Participatory Budgeting Fund https://acvo.org.uk/funding/just-transition-fund/

Maggie drew our attention to this funding opportunity - £333,333 for each local authority area. This capital fund aims to empower local people to shape a Just Transition to net zero reflecting local needs.

Next meeting: 1pm Thursday 17th November.

Agenda to include: presentation on Reuse shop (Andrew/Pam); more on the Just Transition Fund (Maggie); Growing Food end of project report (Steven); update on emissions project (Sinclair).